## Sheet1
Day | Names | Tasks/Components done
Day1 | Basavaraj S Biradar | Signup,MongoDB Connection,App.js
| Anik Saha | Cloud Database creation and connection
| Ankit Dey | Front end,signup and Login
| Sowmyadeep Mandal | Signup,MongoDB Connection,App.js
| Nasrin Begam | Cloud Database creation and connection
| Pavan Kumar NR | Signup,MongoDB Connection,App.js
Day2 | Basavaraj S Biradar | Login,Users Connection,Backend-Frontend Connection
| Anik Saha | Job Posts Routes,Model,Controller
| Ankit Dey | Front End Authentication
| Sowmyadeep Mandal | Logo creation and Login validation
| Nasrin Begam | Job Posts Routes,Postman data check
| Pavan Kumar NR | Signup validation,Testing,Excel and overall monitoring of project
Day3 | Basavaraj S Biradar | Updation in overall code,Jobs page,Back end,overall styling
| Anik Saha | Application,route,Controller and model,Changes in user
| Ankit Dey | Front end Home page and routing,dynamic Job applications
| Sowmyadeep Mandal | Job posts page,Forms,styling and changes in code
| Nasrin Begam | Application,route,Controller and model,Changes in user
| Pavan Kumar NR | Companies page,Job page and other minor updates,Testing webpage
Day 4 | Basavaraj S Biradar | Dashboard and Profile both Front-end and Back-end
| Anik Saha | Home page UI updation,PPT creation
| Ankit Dey | Navbar updation and Back-end changes
| Sowmyadeep Mandal | Job posts page,Job apply page
| Nasrin Begam | Companies page updation and logos
| Pavan Kumar NR | page not found page ,Excel,Testing the webpage

## Sheet2
| Method | Route | Description
AuthRoues.js | POST | /signup | Registers a new user. Calls signupUser controller.
| POST | /login | Logs in a user and returns a JWT token. Calls loginUser controller.
| GET | /user | Protected route. Returns logged-in user info.
| GET | /recruiter/:recruiterId | Fetches all jobs posted by a specific recruiter (by recruiterId).
ApplicationRoutes.js | POST | /applications | Create a new application (requires user ID and job ID).
| GET | /applications/user/:userid | Get all applications submitted by a specific user
| GET | /applications/recruiter/:recruiterId | Get all applications for jobs posted by a specific recruiter.
| GET | /applications/:applicationId/recruiter/:recruiterId | Get a single application if the recruiter posted the related job.
| PATCH | /applications/:applicationId/status | Update the status (pending, accepted, rejected) of an application.